## Epics
Epic ID | Name | Discipline | Goal | Tickets
EPIC 1 | Lexical Backbone & Candidate Edge Generation | Data Pipeline | Produce a scored, evidence-backed set of candidate senses and edges from Open English WordNet + corpus + embeddings, linked to WordNet-derived semantic concepts and validated against a labeled gold set before curation. Nothing here is shown to a learner yet. | LEX-101..107
EPIC 2 | Human Curation Tooling | Backend + Internal Tool | Give a reviewer a working interface to approve, edit, and publish candidate content. No content reaches the public API without passing through this. | CUR-101..103
EPIC 3 | Core Backend & Data Model | Backend | Stand up the FastAPI service and PostgreSQL schema; implement the public read/write API surface. | API-101..106
EPIC 4 | Graph Frontend | Frontend | Build the searchable, explorable graph UI: search, sense panel, edge panel, personal/linguistic view toggle. | FE-101..105
EPIC 5 | Exercise Engine | Full-stack + Content | Build the context-anchored exercise loop and the 'why not' feedback panel; author the first gold-standard exercise set. | EX-101..103
EPIC 6 | Personal Mastery Layer | Backend + Frontend | Implement mastery decay, lightweight per-user identity, and the weak-edges review dashboard. | MAS-101..103
EPIC 7 | MVP Content & Release | Content + DevOps | Scale curated content to MVP targets and ship a public, monitored deployment. | REL-101..103
EPIC 8 | Evaluation | Research | Run the controlled pre/post experiment that produces the diploma's empirical result. | EVAL-101..103

## Backlog
Ticket ID | Epic | Title | Type | Description | Technical Details | Acceptance Criteria | Dependencies | Est. (days) | Priority
LEX-101 | EPIC 1 | Pipeline project skeleton | Data Pipeline | Set up the offline knowledge pipeline as a runnable, config-driven Python package. | Create pipeline/{sources,candidates,scoring,exercises,review} as importable modules. CLI entry point: python -m pipeline.run --stage all¦sources¦candidates¦scoring. Config via pipeline/config.yaml (corpus paths, model names, thresholds). | Repo structure matches the agreed layout. CLI runs end-to-end on a 20-word sample vocabulary without error. Each stage is independently runnable and idempotent (re-run does not duplicate rows). | — | 1 | Must
LEX-102 | EPIC 1 | Import Open English WordNet | Data Pipeline | Load Open English WordNet into normalized staging tables. | Target tables: raw_synsets(id, pos, gloss), raw_senses(id, synset_id, lemma), raw_relations(source_sense_id, target_sense_id, relation_type). Use the official OEWN release (LMF or WN-JSON format), parsed with the nltk or wn Python package. | All synsets for verb/noun/adjective POS load without data loss. Row counts match source release counts (documented in a load-report.txt). Re-running the load (truncate+reload) produces identical row counts. | LEX-101 | 1.5 | Must
LEX-103 | EPIC 1 | Semantic concept linking (WordNet synsets) | Data Pipeline | Link every imported sense to its semantic concept, reusing WordNet's own synset structure instead of building a separate clustering pipeline. | New table semantic_concepts(id, synset_id, definition, source='WordNet'), populated directly from the raw_synsets staging table (LEX-102). Add concept_id foreign key on word_senses referencing semantic_concepts. | Every imported sense in the seed vocabulary is linked to its source WordNet synset/concept via a populated concept_id. Manual spot-check of 10 concepts confirms correct import/mapping (member senses genuinely come from the stated synset) — this is an ETL correctness check, not a claim about interchangeability in context. | LEX-102 | 0.5 | Must
LEX-104 | EPIC 1 | Candidate relation generation | Data Pipeline | Generate candidate typed edges between senses: within the same semantic concept (WordNet's own definition of strict synonymy) and across related concepts, found via embedding-neighborhood search rather than a clustering step. | For each sense: (a) pair it with every other sense sharing its concept_id and label the pair as a SYNONYM candidate — WordNet defines synset co-membership as synonymy, not near-synonymy, so the pipeline must not hedge this; (b) retrieve its top-k (e.g. k=15) nearest neighbors by embedding cosine similarity via pgvector, regardless of concept, as cross-concept candidates, labeled NEAR_SYNONYM / INTENSITY_SHIFT / REGISTER_SHIFT / PARAPHRASE / COLLOCATION_ALTERNATIVE / informational HYPERNYM-HYPONYM from the WordNet relation where one exists, else 'unclassified'. WordNet-derived types are evidence for curator review, never the final published type — WordNet is authoritative for SYNONYM/HYPERNYM/HYPONYM/ANTONYM only; REGISTER_SHIFT, INTENSITY_SHIFT, PARAPHRASE, and COLLOCATION_ALTERNATIVE always require corpus or curator confirmation. Store raw semantic_similarity per candidate. Output candidate_edges(source_sense_id, target_sense_id, edge_type_guess, semantic_similarity, status='candidate'). | At least 5 ranked candidates generated per sense in the seed vocabulary, combining same-concept (SYNONYM) and cross-concept sources. Manual spot-check on a random 30-pair sample shows ≥70% judged plausible. No candidate is auto-labeled NEAR_SYNONYM, REGISTER_SHIFT, or PARAPHRASE solely because semantic_similarity is high without a corresponding WordNet or corpus signal (guards against high-similarity-but-not-substitutable pairs such as car/vehicle). | LEX-103 | 2 | Must
LEX-105 | EPIC 1 | Context / collocation evidence extraction | Data Pipeline | Extract collocation frequency evidence per candidate edge from a target corpus. | Dependency-parse a corpus subset (e.g., academic-register Wikipedia sample or a public academic corpus) with spaCy en_core_web_lg. Extract verb+object and noun+modifier pairs. Populate collocation_evidence(edge_id, pattern, frequency). | For at least 15 seed verbs, the table contains the top-10 objects by frequency, verifiable by a manual query against 3 spot-checked verbs. | LEX-104 | 2 | Should
LEX-106 | EPIC 1 | Base substitutability scoring | Data Pipeline | Compute a curated base_substitutability per candidate edge, distinct from raw semantic_similarity, so that closeness in meaning is not confused with the ability to substitute. | Implement pipeline/scoring/base_score.py: base_substitutability = f(semantic_similarity, edge_type_guess, collocation_evidence) using the documented POS-dependent weighted formula, with type-based caps read from a config file (pipeline/config/relation_caps.yaml, e.g. HYPERNYM: 0.4, HYPONYM: 0.4) rather than hardcoded in the scoring function, so the evaluation stage (LEX-107) can test different cap values. Write both semantic_similarity and base_substitutability to candidate_edges. | Unit test confirms a high-similarity hypernym-type test fixture (car/vehicle-style pair) receives base_substitutability below the configured cap while semantic_similarity remains high. Changing a value in relation_caps.yaml changes scoring output without a code change. Scores are deterministic given fixed inputs. | LEX-104, LEX-105 | 1.5 | Must
LEX-107 | EPIC 1 | Candidate validation dataset | Data Pipeline + Research | Build a small human-labeled gold set of sense pairs to validate the scoring pipeline's precision before scaling curation. | 50–100 sense pairs manually labeled with true edge type and a reference substitutability judgment (0–1), independent of the pipeline's own output; store as evaluation/golden_set/pipeline_pairs.csv. Compare pipeline output against these labels (edge-type precision/recall; substitutability mean absolute error). | Golden set has ≥50 labeled pairs, double-checked by a second reviewer. Evaluation report (precision/recall + MAE) is produced and reviewed before CUR-101 begins reviewing content at scale. | LEX-106 | 1.5 | Should
CUR-101 | EPIC 2 | Curation review tool | Backend + Internal Tool | Build an internal admin interface for reviewing candidate clusters and edges. | FastAPI + server-rendered HTML (Jinja2) or a small Streamlit app, restricted to internal auth (basic auth is acceptable for MVP). List candidate_edges sorted by base_substitutability descending, grouped by semantic concept with cross-concept candidates flagged separately, showing both semantic_similarity and base_substitutability side by side; actions: approve / edit score / edit edge type / reject; edits write to lexical_edges with curator_status. | Reviewer can approve an edge, edit its score or type, and add/remove example sentences. curator_status transitions to 'reviewed' on approval. Every action is logged with reviewer_id and timestamp in a curation_log table. The pipeline evaluation report from LEX-107 is visible to the reviewer before they approve at scale. | LEX-106, LEX-107 | 2 | Must
CUR-102 | EPIC 2 | Context rule authoring form | Backend + Internal Tool | Add a form for authoring context rules attached to a reviewed edge, including the explanation text used later in learner-facing 'why not' responses. | Form fields: frame (free text), subject_type, object_type, register, explanation (curator-authored text shown when a learner picks a poor fit for this context), ≥1 valid example, ≥1 invalid example. Saves to context_rules linked by edge_id. | Form rejects submission if required fields (frame, explanation, ≥1 valid + ≥1 invalid example) are missing. Saved rows are retrievable via GET /api/edges/{id}/suitability (see API-104) and via POST /api/why-not (see API-105). | CUR-101, API-104 | 1.5 | Must
CUR-103 | EPIC 2 | Publish & versioning workflow | Backend + Internal Tool | Bundle reviewed content into a versioned, publishable release. | Publish action creates a content_versions row (semantic version, e.g. 0.1.0), sets curator_status='published' on all eligible edges/rules/exercises, and stamps their graph_version_id. Any published exercise whose edge changes after this point is flagged needs_review. | Publishing increments the version number. Flagged exercises appear in a queryable 'needs review' list. The public API (Section EPIC 3) only ever serves rows with curator_status='published'. | CUR-102 | 2 | Must
API-101 | EPIC 3 | Backend project scaffold | Backend | Initialize the FastAPI service with ORM, migrations, and local dev environment. | FastAPI + Pydantic v2 + SQLAlchemy 2.0 + Alembic. docker-compose.yml with api + postgres:15 services. GET /health returns {'status':'ok'}. | docker-compose up starts both services. alembic upgrade head creates every table from the domain model (Section 3 of the architecture chapter) without error. /health returns 200. | — | 1 | Must
API-102 | EPIC 3 | Search endpoint | Backend | Implement sense search with fuzzy matching. | GET /api/search?q=. Postgres full-text search + pg_trgm extension for typo tolerance. Returns list of {senseId, lemma, pos, gloss} ranked by frequency_rank. | Query 'improve' returns all senses of 'improve' in <200ms on a 500-sense dataset. Query 'imporve' (typo) still returns a result via trigram similarity ≥0.3. | API-101, CUR-103 | 1.5 | Must
API-103 | EPIC 3 | Graph neighborhood endpoint | Backend | Implement retrieval of a sense's local graph neighborhood. | GET /api/senses/{senseId}/graph?depth=&relation_types=&mode=. Adjacency-table traversal (recursive CTE for depth≤2), no ORM lazy-loading N+1 queries. | depth=1 returns only directly connected edges. relation_types filter excludes non-matching types. Response time <300ms for depth=2 on the published MVP dataset. | API-102 | 2 | Must
API-104 | EPIC 3 | Edge suitability endpoint | Backend | Implement contextual suitability scoring for a specific sentence. | GET /api/edges/{edgeId}/suitability?context_sentence=. Matches the sentence against stored context_rules (frame/object-type match), applies the C(E,x) formula (Section 2 of the architecture chapter). Response shape: {score, dimensions: {semantic, grammar, collocation, register, naturalness}, matched_rule, confidence} — individual dimensions may be null when not measurable for the given context; the response never fabricates a value for an unmeasurable dimension. | For a documented golden-set case (improve→enhance + 'skills'), returned scores match the manually verified value within 0.02 tolerance. Unmatched context returns suitability=null with a clear reason field, not a 500 error. A context with a partially-measurable dimension returns null for that dimension and a correspondingly reduced confidence value, not a guessed number. | API-103, CUR-102 | 2.5 | Must
API-105 | EPIC 3 | Attempt & why-not endpoints | Backend | Implement exercise submission scoring and the why-not explanation endpoint. | POST /api/attempts {exerciseId, selectedSenseId} → scores against exercise.correctSenseIds/partialSenseIds, classifies the result with a reason code (WRONG_SENSE, WRONG_GRAMMAR, WRONG_PREPOSITION, WRONG_COLLOCATION, WRONG_REGISTER, WRONG_INTENSITY, PARTIAL_MEANING, UNNATURAL, VALID_BUT_LESS_APPROPRIATE), writes to attempts, triggers edge/context mastery update (see MAS-101). POST /api/why-not {sentence, targetSenseId, selectedSenseId} → computes the why-not response at request time from the Attempt's reason code plus the matched ContextRule's authored explanation field and valid examples — there is no separate why_not_entries table. | Correct submission returns status='correct' and updates edge_mastery and context_mastery. Incorrect/partial submission returns a why-not response with a non-empty betterOptions list and a populated reason code, reproducible from the stored ContextRule and Attempt alone (no hidden state elsewhere). | API-104, MAS-101 | 2 | Must
API-106 | EPIC 3 | Integration test suite + CI | Backend | Cover all API endpoints with automated tests and wire up CI. | pytest + httpx against a seeded test database (fixtures for senses/edges/rules/exercises). GitHub Actions workflow running the suite on every pull request. | CI runs on every PR. Test coverage ≥80% on the api/ package. A PR cannot merge with a failing suite (branch protection rule). | API-105 | 2 | Should
FE-101 | EPIC 4 | Frontend scaffold | Frontend | Initialize the Next.js application. | Next.js 14 + TypeScript + Tailwind CSS + TanStack Query. Base layout, environment-based API URL config. | npm run dev serves a page that successfully calls /api/search and renders the raw JSON response. | API-102 | 1 | Must
FE-102 | EPIC 4 | Search & sense-disambiguation screen | Frontend | Build the search entry point with sense selection. | Debounced search input → GET /api/search; dropdown list of matching senses with short glosses (per Section 18.1 UX spec); selecting a sense navigates to /graph/[senseId]. | Typing 'implement' shows a dropdown of its senses. Selecting one navigates to the graph screen and updates the URL to include the senseId. | FE-101 | 1.5 | Must
FE-103 | EPIC 4 | Graph visualization screen | Frontend | Build the interactive node-and-edge graph view. | Cytoscape.js rendering GET /api/senses/{id}/graph output. Center node + neighbors; POS color-coding; edge thickness mapped to global_substitutability; click-to-recenter. | Graph renders within 500ms for a 20-node neighborhood. Clicking a neighbor node re-centers the graph on it and updates the route. | FE-102, API-103 | 3 | Must
FE-104 | EPIC 4 | Sense & edge detail panels | Frontend | Build the side panels shown on node/edge click. | Sense panel: definition, CEFR, examples, strong/weak alternatives (per Section 18.3). Edge panel: type, global score, best contexts, transformation note, personal mastery (per Section 18.4). | Panel content matches API response fields exactly, with no placeholder text in production. Panel closes on outside click or Escape key. | FE-103, API-104 | 2 | Must
FE-105 | EPIC 4 | Linguistic / personal view toggle | Frontend | Let the user switch the graph between global and personal mastery coloring. | Toggle control calls GET /api/mastery/overlay?senseId= when 'personal' is active (requires MAS-102 identity); recolors edges per the mapping table in the architecture chapter (green/amber/orange/red/gray). | With no attempt history, personal view shows all edges gray ('unpracticed'). After one correct attempt, the corresponding edge shows green on next load. | FE-104, MAS-101, MAS-102 | 2 | Should
EX-101 | EPIC 5 | Minimal-pair exercise screen | Full-stack | Build the primary exercise type: choose the best word for a blanked sentence. | Renders exercise.prompt + exercise.options (per Section 9.1); submits selection via POST /api/attempts; displays exercise.explanation on response. | Correct, incorrect, and partial states each render a visually distinct result (color + icon). Explanation text is displayed exactly as returned by the API, no client-side rewriting. | API-105, FE-101 | 2 | Must
EX-102 | EPIC 5 | 'Why not' feedback panel | Full-stack | Build the panel that explains an incorrect or partial choice. | Triggered on incorrect/partial submission; calls POST /api/why-not; renders headline + explanation + betterOptions (per Section 9.2). Also triggers a graph recolor event consumed by FE-105 without a full page reload. | Panel is visually distinct (amber/red accent) and dismissible. Submitting a second exercise correctly recolors the graph within the same session, no reload required. | EX-101, API-105, FE-105 | 2 | Must
EX-103 | EPIC 5 | Author first gold-standard exercise set | Content | Manually author the first 20–30 exercises for the pilot vocabulary. | Use CUR-101/CUR-102 tooling. Each exercise: ≥3 distractors, a written why-not explanation per distractor, ≥1 valid + ≥1 invalid example sentence on the underlying context rule. | All 20–30 exercises have a second reviewer's sign-off (reviewedBy populated) before curator_status is set to 'published'. | CUR-102, EX-101 | 3 | Must
MAS-101 | EPIC 6 | Mastery decay & update logic | Backend | Implement the edge/context mastery update triggered by each attempt. | Implement M(E,u,t) = α·M(E,u,t′)·2^(−Δt/H) + (1−α)·attempt_score with H=14 (a true 14-day half-life — not e^(−Δt/14), whose actual half-life is ≈9.7 days) and α=0.75 as a configurable, not hardcoded, prototype hyperparameter (Section 2 of the architecture chapter). Apply to edge_mastery keyed by (user, edge) and separately to context_mastery keyed by (user, edge, context_rule_id) — not a generic 'context' label — on every POST /api/attempts. | Unit test reproduces a documented worked example (e.g. skills 92%, quality 89%, situation 51%) given a scripted attempt history and time deltas, within floating-point tolerance. A second unit test confirms decay(t=14 days) == 0.5 exactly, verifying the half-life is actually 14 days. | API-105 | 1.5 | Must
MAS-102 | EPIC 6 | Lightweight user identity | Backend | Add minimal per-user identity without building full account infrastructure. | Anonymous device-scoped ID (signed cookie / localStorage token) for MVP, upgradeable later to email + magic link. No plaintext credentials stored. | A returning user on the same browser sees their prior mastery state across sessions. Schema contains no password field for the MVP identity path. | API-101 | 1.5 | Should
MAS-103 | EPIC 6 | Weak-edges review dashboard | Frontend + Backend | Build the view showing a user's edges due for review. | GET /api/mastery/overlay returns edges with confidence <0.5 and nextReviewAt in the past; frontend lists them sorted by nextReviewAt ascending, linking directly to a targeted exercise. | An edge with confidence <0.5 and a past-due nextReviewAt appears at the top of the list. Clicking an item opens an exercise targeting that specific edge. | MAS-101, FE-105 | 2 | Should
REL-101 | EPIC 7 | Scale content to MVP targets | Content + Data Pipeline | Run the LEX→CUR pipeline across the full MVP vocabulary scope. | Extend seed vocabulary to the MVP target (300–500 senses, 1,000–2,000 edges, 100–300 exercises), all routed through the same pipeline and curation steps as the pilot. | Random 10% sample of published content shows ≥90% reviewer agreement with the recorded scores on a second-pass audit. | LEX-105, CUR-103, EX-103 | 5 | Must
REL-102 | EPIC 7 | Public deployment & monitoring | DevOps | Deploy the application to a public, monitored environment. | Deploy API + Postgres + frontend to a free/low-cost host (e.g., Fly.io / Render + managed Postgres). HTTPS via the host's managed certs. Uptime monitoring (e.g., UptimeRobot) on /health and the public homepage. | Public URL is reachable and serves the app. Monitoring alerts fire on a simulated downtime test. Deployment is reproducible from a documented docker-compose.prod.yml and a short runbook. | API-106, FE-105, REL-101 | 2 | Must
REL-103 | EPIC 7 | Onboarding / landing flow | Frontend | Build a short landing explanation of what the tool does differently. | Single landing view stating the core positioning (Section 2 of the development-plan chapter); a clear 'Try it' path straight into a search or a sample exercise. | A first-time visitor can go from the landing page to a completed exercise in ≤3 clicks, verified by a manual click-through test. | REL-102, EX-101 | 1 | Should
EVAL-101 | EPIC 8 | Pre/post test instrument | Research | Design the evaluation instrument for the controlled experiment. | 20–30 contextual vocabulary questions, held outside the main app (e.g., a separate form), covering the same vocabulary scope as the MVP content. | Instrument reviewed by an academic advisor or peer for face validity before use; reviewer sign-off recorded. | REL-101 | 2 | Must
EVAL-102 | EPIC 8 | Attempt logging for analysis | Backend | Instrument the app to export analysis-ready attempt data. | Extend the attempts table / add an export job producing one CSV row per attempt: participant id, group (control/experimental), accuracy, contextual appropriateness, time-per-task, timestamp. | Exported CSV contains every field needed for the diploma's planned statistics (Section 7 of the relevance-analysis chapter), verified against a 3-row manual spot check. | MAS-101, EVAL-101 | 1.5 | Must
EVAL-103 | EPIC 8 | Run controlled comparison & compute results | Research | Execute the pre-test / practice-period / post-test comparison and compute the headline results. | Recruit 10–30 participants split into control (conventional synonym exercises) and experimental (this system) groups; run the instrument and a 5–10 session practice period. Compute ΔAccuracy = PostTest − PreTest per group, then Effect = ΔExperimental − ΔControl as the primary result. Compute secondary metrics: contextual appropriateness, retention (accuracy at 1/7/30 days), repeated-error rate, time-per-task, and reason-code frequency breakdown (from the Attempt log, e.g. WRONG_COLLOCATION vs WRONG_REGISTER rates) for the experimental group. | Results file and summary statistics produced, including the Effect figure and the reason-code frequency table; a second, independent recomputation from the raw exported logs matches the reported numbers exactly. | EVAL-102, EX-103 | 5 | Must